## Sheet1
What went well | What went poorly | What ideas do you have | How should we take action
Successfully imported the heart disease dataset from the UCI Machine Learning Repository. | LSTM model required significant hyperparameter tuning, leading to delays. | Use automated hyperparameter tuning techniques to optimize LSTM training. | Use libraries like Optuna or GridSearchCV for automated hyperparameter tuning.
Preprocessing module was implemented efficiently, improving data quality for model training. | Handling imbalanced datasets posed a challenge for accurate predictions. | Implement data augmentation techniques to balance the dataset and improve model performance. | Employ SMOTE or undersampling techniques to address class imbalance.
FNN, LSTM, and XGBoost models were trained successfully, with promising initial results. | Performance optimization for the API needed additional effort due to high latency. | Optimize API response times by reducing unnecessary computations. | Profile API performance and implement caching where necessary.
Heart disease prediction API was developed and integrated successfully. | Deployment on cloud infrastructure faced security and scalability issues. | Ensure early testing and security audits for cloud deployment. | Adopt best security practices and conduct vulnerability testing before deployment.
Online portal was designed with a user-friendly interface and API connectivity. | Some features in the visualization dashboard took longer than expected to implement. | Break visualization features into smaller tasks for faster delivery. | Refine the sprint planning process to allocate proper time for visualization improvements.